## How to use this file
Date | Version | Author | Content
2016-05-13 | 1 | Michel Stahl | This is an example for software release criteria. It is based on work done together with Akira Ueno, on Oct 2007
How to use this file
This file contains examples for Product Quality release criteria (QRC). There are two flavors: One flavor has criteria for each milestone (sheets pre-Alpha, Alpha, Beta, Gold) and one flavor has all the criteria in one large table ("Shorter, One-page option" sheet). The short option is indeed shorter - it contains less release criteria. Both options can be used as-is or edited and changed to fit your situation. In such case they are just a good start. Some criteria need a defined limit (e.g. Number of Critical severity bugs). Since the value would change for each product and organization, I just put "<X" or ">Y%". The user of these criteria lists need to put a real number there. Note that the same place holder ("X") may appear in the Alpha, Beta, Gold criteria. This does not mean it needs to be the SAME value for all milestones; more likely, the number need to be different. The "X" is a place holder for you to replace with a correct number. This list does not guarantee anything. You can meet all the criteria you put in place and still have a bad product. Your requirements, tests, limits may all be off. All these lists do is serve as a guideline for creating SW Release Criteria and as a tool for tracking how well you met the criteria. Feel free to add or remove lines or criteria. These QRCs may be missing items critical to your product. They most likely include items that are irrelevant to your product. The longer-option lists (sheets pre-alpha, alpha etc.) were designed to be used not only when assessing a release. They should be used on a weekly basis to assess if you are getting closer to meet the release criteria. I did my best to avoid mistakes (typos, silly or serious oversights). I hope I managed, but again.... no guarantee. Comments? Send me a note. Michael Stahl May 2016 michael.m.stahl@gmail.com www.testprincipia.com
All rights reserved © Michael Stahl 2016

## Pre-Alpha
| Milestone | Program | Release date goal
| Pre-Alpha | <program name> | <ww date>
Owner | Function | Requirement | Metric | Status | Goal
| HW | HW Available and functional | HW status
| HW |  | Number of system required by development and validation for pre-Alpha |  | <number>
| HW |  | % of requested systems that are available |  | 100%
| HW |  | % of HW features needed to support pre-Alpha features that are functional |  | 100%
| HW |  | HW is stable enough to conduct pre-Alpha testing |  | Done
| SW | All features planned for pre-alpha are "code complete" | Feature development status
| SW |  | % of Pre-Alpha features coded and merged into the main branch |  | 100%
| SW |  | % of Pre-Alpha features pass unit level testing |  | 100%
| SW |  | % of Integration tests PASSED (on pre-Alpha target Operating Systems) |  | 100%
| SW |  | Formal code inspection complete |  | Done
| SW |  | Static analysis complete; All errors and warnings reviewed and dispositioned |  | Done
| SW |  | Unit level testing reports for all pre-alpha features published |  | Done
| SW |  | Integration test report published |  | Done
| SW |  | Formal code inspection report published |  | Done
| Localization | The GUI supports the languages targeted for pre-alpha | % of supported languages
| Localization |  | Number of languages planned to be supported by pre-Alpha |  | <number>
| Localization |  | % of the languages that are supported |  | 100%
| Performance | Performance is meeting the pre-alpha targets | % of Gold release goal(1)
| Performance |  | ... Add lines for different performance parameters that are of interest for your product(2) |  | Meeting the goal
| Regulatory | Regulatory testing planned and executed | Regulatory test status
| Regulatory |  | External testing facility identified and engaged |  | Done
| Regulatory |  | % Regulatory (internal) testing complete |  | 100%
| Regulatory |  | Internal regulatory test report (including gap analysis) published |  | Done
| Regulatory |  | Corrective action published (if necessary) |  | Done
| Validation | Validation planning complete | Validation planning status
| Validation |  | Project level test plan completed, reviewed and approved |  | Done
| Validation |  | # of feature-level test plans planned for pre-alpha features |  | <number>
| Validation |  | % of feature-level test plans that are completed, reviewed and approved |  | 100%
| Validation |  | Test cases for all pre-alpha features developed, loaded to test management system, reviewed and approved |  | Done
| Validation | All tests are traceable to product requirements | % of test cases mapped to product requirement |  | 100%
| Validation | < X% failing / blocked tests per new feature | Test execution status - new features
| Validation |  | Total number of new features targeted for pre-Alpha |  | <number>
| Validation |  | Number of new pre-Alpha features tested |  | All pre-alpha features
| Validation |  | Number of new pre-Alpha features completely blocked |  | 0
| Validation |  | Number of new pre-Alpha features with fail / block rate > 75% |  | <number>
| Validation |  | Number of new pre-Alpha features with fail / block rate between 50% and 75% |  | <number>
| Validation |  | Number of new pre-Alpha features with fail / block rate between 25% and 50% |  | <number>
| Validation |  | Number of new pre-Alpha features with fail / block rate < 25% |  | <number>
| Validation | < Y% failing / blocked tests per legacy feature(3) | Test execution status - legacy features
| Validation |  | Total number of legacy features targeted for pre-Alpha |  | <number>
| Validation |  | Number of legacy pre-Alpha features tested |  | All pre-alpha features
| Validation |  | Number of legacy pre-Alpha features completely blocked |  | 0
| Validation |  | Number of legacy pre-Alpha features with fail / block rate > 75% |  | <number>
| Validation |  | Number of legacy pre-Alpha features with fail / block rate between 50% and 75% |  | <number>
| Validation |  | Number of legacy pre-Alpha features with fail / block rate between 25% and 50% |  | <number>
| Validation |  | Number of legacy pre-Alpha features with fail / block rate < 25% |  | <number>
| Validation | Validation report published | Validation pre-Alpha status report published |  | Done
| External Documentation | All External Documents are at accuracy level requested by marketing for pre-Alpha | External documents status
| External Documentation |  | Number of external documents needed for pre-Alpha |  | <number>
| External Documentation |  | % of pre-alpha external documents ready for release |  | 100%
| Internal Documentation | All Engineering Documents are completed for Pre-Alpha features and post review for all other features | Engineering documents status(4)
| Internal Documentation |  | # of documents planned for pre-Alpha |  | <number>
| Internal Documentation |  | % of documents planned for pre-Alpha completed |  | 100%
| Internal Documentation |  | # of documents planned for the project |  | <number>
| Internal Documentation |  | % of documents planned for the project that completed review |  | 100%
| Build & Release | Build & Release systems are in place | Build & Release systems status
| Build & Release |  | Release labeled and virus scanned |  | Done
| Build & Release |  | Source control in place |  | Done
| Build & Release |  | Continuous Integration in place |  | Done
| Build & Release |  | % pre-alpha features that have CI tests |  | <number>
| Build & Release |  | ... Add lines for other infrastructure elements used in your organization |  | Meeting the goal
| Customer Support | Customer support is prepared for the release | Customer support preparation status
| Customer Support |  | Support plan created, reviewed and published |  | Done
| Customer Support |  | Customer support resources allocated and trained on pre-Alpha features |  | Done
| Customer Support |  | Release notes drafted, reviewed and ready for publication |  | Done
| Customer Support |  | ... Add lines for other documents or tools needed by customer support in your organization |  | Done
Notes
| 1 | May also be stated as real goal (e.g. < 30mSec; > 10mbps; etc.)
| 2 | For example: throughput; transaction time; CPU utilization; memory utilization; power consumption; etc.
| 3 | The percentage goal should be lower if this is a maintenance release VS an upgrade release
| 4 | Consider listing the different document types (requirement, design, architecture etc..) and for tracking at higher granularity
All rights reserved © Michael Stahl 2016

## Alpha
| Milestone | Program | Release date goal
| Alpha | <program name> | <ww date>
Owner | Function | Requirement | Metric | Status | Goal
| PLC | All requirements from previous milestone continue to be satisfied | Pre-Alpha Requirements status
| PLC |  | All Pre-Alpha Release Requirements are met |  | Done
| PLC |  | All waivers granted at Pre-Alpha are closed (requirement are now met) |  | Done
| HW | HW is Feature Complete and Fully Functional on alpha-target SKU | Feature support status
| HW |  | Total # features planned |  | <number>
| HW |  | # features blocked by HW |  | 0
| HW |  | % of features blocked by HW |  | 0%
| HW | HW Test Execution | HW test execution status
| HW |  | All HW tests (including Q&R) performed |  | Done
| HW |  | All HW test reports published |  | Done
| HW |  | All HW issues filed |  | Done
| HW | HW Quality | HW bugs status: Number of Critical and High severity HW issues open
| HW |  | # open Critical HW issues |  | <X
| HW |  | # open High severity HW issues |  | <Y
|  |  | # of open HW issues (total number) |  | <Z
| SW | All features planned for alpha are "code complete" | Feature development status
| SW |  | % of Alpha features that are coded and merged into the main branch |  | 100%
| SW |  | % of Alpha features pass unit level testing |  | 100%
| SW |  | % of Integration tests PASSED (on all Alpha target Operating Systems) |  | 100%
| SW |  | Formal code inspection complete |  | Done
| SW |  | Static analysis complete; All errors and warnings reviewed and dispositioned |  | Done
| SW |  | Unit level testing reports for all product features published |  | Done
| SW |  | Integration test report published |  | Done
| SW |  | Formal code inspection report published |  | Done
| Validation | Full backward compatibility to previous generation HW | Tested on all supported HW |  | Done
| Localization | The GUI supports the languages targeted for alpha | % of supported languages
| Localization |  | Number of languages planned to be supported by Alpha |  | <number>
| Localization |  | % of the languages that are supported |  | 100%
| Performance | Performance is meeting the alpha targets | % of Gold release goal(1)
| Performance |  | ... Add lines for different performance parameters that are of interest for your product(2) |  | Meeting the goal
| Regulatory | External regulatory testing cycle completed | Regulatory test status
| Regulatory |  | % Regulatory testing complete |  | 100%
| Regulatory |  | Regulatory test report (including gap analysis) published |  | Done
| Regulatory |  | Corrective action published (if necessary) |  | Done
| Validation | Test plans complete | Test planning status
| Validation |  | project level test plan updated, reviewed and published |  | Done
| Validation |  | # of feature-level test plans planned for alpha features |  | <number>
| Validation |  | % of feature-level test plans that are completed, reviewed and approved |  | 100%
| Validation | All tests are traceable to product requirements | % of test cases mapped to product requirement |  | 100%
| Validation | Full test cycles completed | Test cycle and OS/HW combination test coverage status
| Validation |  | # of tests planned |  | <number>
| Validation |  | % of planned tests that were completed |  | 100%
| Validation |  | Number of different OS-Platform-SKU combinations that were planned to be covered on alpha test cycles |  | <number>
| Validation |  | % of different alpha-target OS-Platform-SKU combinations that were tested |  | 100%
| Validation | < X% failing / blocked tests per new feature | Test execution status - new features(3)
| Validation |  | Total number of new features targeted for Alpha |  | <number>
| Validation |  | Number of new Alpha features tested |  | All alpha features
| Validation |  | Number of new Alpha features completely blocked |  | 0
| Validation |  | Number of new Alpha features with fail / block rate > 75% |  | <number>
| Validation |  | Number of new Alpha features with fail / block rate between 50% and 75% |  | <number>
| Validation |  | Number of new Alpha features with fail / block rate between 25% and 50% |  | <number>
| Validation |  | Number of new Alpha features with fail / block rate < 25% |  | <number>
| Validation | < Y% failing / blocked tests per legacy feature | Test execution status - legacy features(4)
| Validation |  | Total number of legacy features targeted for Alpha |  | <number>
| Validation |  | Number of legacy Alpha features tested |  | All alpha features
| Validation |  | Number of legacy Alpha features completely blocked |  | 0
| Validation |  | Number of legacy Alpha features with fail / block rate > 75% |  | <number>
| Validation |  | Number of legacy Alpha features with fail / block rate between 50% and 75% |  | <number>
| Validation |  | Number of legacy Alpha features with fail / block rate between 25% and 50% |  | <number>
| Validation |  | Number of legacy Alpha features with fail / block rate < 25% |  | <number>
| Validation | < X critical bugs | Critical severity bug count |  | <number>
| Validation | < Y High severity bugs | High severity bug count |  | <number>
| Validation | < Z total bugs | Total bug count |  | <number>
| Validation | Specific features test & bug counts | % test execution completed and bug count for specific features
| Validation |  | <add lines as needed for features for which there are specific quality requirements. E.g. "100% tests executed and no critical or High severity bugs on Install/Uninstall" > |  | Meeting the goal
| Validation | Validation report published | Validation Alpha status report published |  | Done
| External Documentation | All External Documents are at accuracy level requested by marketing for Alpha | External documents status
| External Documentation |  | # of external pre-Alpha documents that needs updating |  | <number>
| External Documentation |  | % of external pre-Alpha documents updated |  | 100%
| External Documentation |  | Number of external documents needed for Alpha |  | <number>
| External Documentation |  | % of alpha external documents ready for release |  | 100%
| Internal Documentation | All Engineering Documents are at completed for Alpha features | Engineering documents status(5)
| Internal Documentation |  | # of pre-Alpha documents that needs updating |  | <number>
| Internal Documentation |  | % of pre-Alpha documents updated |  | 100%
| Internal Documentation |  | # of documents planned for Alpha |  | <number>
| Internal Documentation |  | % of documents planned for Alpha completed |  | 100%
| Build & Release | Build & Release systems are in place | Build & Release systems status
| Build & Release |  | Release labeled and virus scanned |  | Done
| Build & Release |  | % alpha features that have CI tests |  | <number>
| Build & Release |  | ... Add lines for other infrastructure elements used in your organization |  | Meeting the goal
| Customer Support | Customer support is prepared for the release | Customer support preparation status
| Customer Support |  | Support plan updated, reviewed and published |  | Done
| Customer Support |  | Customer support resources allocated and trained on Alpha features |  | Done
| Customer Support |  | Release notes drafted, reviewed and ready for publication |  | Done
| Customer Support |  | ... Add lines for other documents or tools needed by customer support in your organization |  | Meeting the goal
Notes
| 1 | May also be stated as real goal (e.g. < 30mSec; > 10mbps; etc.)
| 2 | For example: throughput; transaction time; CPU utilization; memory utilization; power consumption; etc.
| 3 | Decide where to lump pre-Alpha new features. They can go together with the Alpha features (that is, track here all new features for this release); the can be lumped with the Legacy features; they can get their own rows with tighter targets than Alpha new features.
| 4 | The percentage goal should be lower if this it a maintenance release VS an upgrade release
| 5 | Consider listing the different document types (requirement, design, architecture etc..) and for tracking at higher granularity
All rights reserved © Michael Stahl 2016

## Beta
| Milestone | Program | Release date goal
| Beta | <program name> | <ww date>
Owner | Function | Requirement | Metric | Status | Goal
| PLC | All requirements from previous milestone continue to be satisfied | Alpha Requirements status
| PLC |  | All Alpha Release Requirements are met |  | Done
| PLC |  | All waivers granted at Alpha are closed (requirement are now met) |  | Done
| HW | HW is Feature Complete and Fully Functional on beta-target SKU | Feature support status
| HW |  | Total # features planned |  | <number>
| HW |  | # features blocked by HW |  | 0
| HW |  | % of features blocked by HW |  | 0%
| HW | HW Test Execution | HW test execution status
| HW |  | All HW tests (including Q&R) performed |  | Done
| HW |  | All HW test reports published |  | Done
| HW |  | All HW issues filed |  | Done
| HW | HW Quality | HW bugs status: Number or Critical and High severity HW issues open
| HW |  | # open Critical HW issues |  | <X
| HW |  | # open High HW issues |  | <Y
|  |  | # of open HW issues (total number) |  | <Z
| HW | HW bug discovery trends down | HW bug trends over last X weeks
| HW |  | # of new bugs opened in the last X weeks is trending down (each week less than the previous week) |  | Yes
| HW |  | Total number of HW bugs is trending down |  | Yes
| SW | All features are "code complete", including all Design Change Requests (DCRs) | Feature development status
| SW |  | % of product features and DCRs that are coded and merged into the main branch |  | 100%
| SW |  | % of product features pass unit level testing |  | 100%
| SW |  | % of Integration tests PASSED (on all target Operating Systems) |  | 100%
| SW |  | Formal code inspection complete |  | Done
| SW |  | Static analysis complete; All errors and warnings reviewed and dispositioned |  | Done
| SW |  | Unit level testing reports for all product features published |  | Done
| SW |  | Integration test report published |  | Done
| SW |  | Formal code inspection report published |  | Done
| SW |  | All debug and test code removed or hidden |  | Done
| Validation | Full backward compatibility to previous generation HW | % of supported HW that was tested |  | 100%
| Localization | Localization of all GUI, User Guides Help and support tools that are planned to be localized, is completed. | Localization status
| Localization |  | Number of languages planned to be supported by the final product |  | <number>
| Localization |  | % of the languages that are supported |  | 100%
| Localization |  | % of localized builds (including GUI, User Guides and Help) validated for both translation accuracy and functionality under localized OS |  | 100%
| Localization |  | Number of product support tools to be localized |  | <number>
| Localization |  | % of product support tools that are localized |  | 100%
| Performance | Performance is meeting the beta targets | % of Gold release goal(1)
| Performance |  | ... Add lines for different performance parameters that are of interest for your product(2) |  | Meeting the goal
| Regulatory | External regulatory testing cycle completed | Regulatory test status
| Regulatory |  | % Regulatory testing complete |  | 100%
| Regulatory |  | Regulatory test report (including gap analysis) published |  | Done
| Regulatory |  | Corrective action published (if necessary) |  | Done
| Validation | All Test plans completed and updated to reflect approved DCRs | Test planning status
| Validation |  | project level test plan updated, reviewed and published |  | Done
| Validation |  | # of feature-level test plans planned for beta features |  | <number>
| Validation |  | % of feature-level test plans that are completed, reviewed and approved |  | 100%
| Validation |  | # of DCR approved and call for an update of test plans |  | <number>
| Validation |  | % of DCR-related updates to test plans that are completed, reviewed and approved |  | 100%
| Validation | All tests are traceable to product requirements | % of test cases mapped to product requirement |  | 100%
| Validation | Full test cycles completed | Test cycle and OS/HW combination test coverage status
| Validation |  | # of tests planned |  | <number>
| Validation |  | % of planned tests that were completed |  | 100%
| Validation |  | Number of different OS-Platform-SKU combinations that were planned to be covered on beta test cycles |  | <number>
| Validation |  | % of different beta-target OS-Platform-SKU combinations that were tested |  | 100%
| Validation | < X% failing / blocked tests per new feature | Test execution status - new features(3)
| Validation |  | Total number of new features targeted for Beta |  | <number>
| Validation |  | Number of new Beta features tested |  | All the product's new features
| Validation |  | Number of new Beta features completely blocked |  | 0
| Validation |  | Number of new Beta features with fail / block rate > 75% |  | <number>
| Validation |  | Number of new Beta features with fail / block rate between 50% and 75% |  | <number>
| Validation |  | Number of new Beta features with fail / block rate between 25% and 50% |  | <number>
| Validation |  | Number of new Beta features with fail / block rate < 25% |  | <number>
| Validation | < Y% failing / blocked tests per legacy feature | Test execution status - legacy features(4)
| Validation |  | Total number of legacy features targeted for Beta |  | <number>
| Validation |  | Number of legacy Beta features tested |  | All the product's legacy features
| Validation |  | Number of legacy Beta features completely blocked |  | 0
| Validation |  | Number of legacy Beta features with fail / block rate > 75% |  | <number>
| Validation |  | Number of legacy Beta features with fail / block rate between 50% and 75% |  | <number>
| Validation |  | Number of legacy Beta features with fail / block rate between 25% and 50% |  | <number>
| Validation |  | Number of legacy Beta features with fail / block rate < 25% |  | <number>
| Validation | < X critical bugs | Critical severity bug count |  | <number>
| Validation | < Y High severity bugs | High severity bug count |  | <number>
| Validation | < Z total bugs | Total bug count |  | <number>
| Validation | Specific features test & bug counts | % test execution completed and bug count for specific features
| Validation |  | <add lines as needed for features for which there are specific quality requirements. E.g. "100% tests executed and no critical or High severity bugs on Install/Uninstall" > |  | Meeting the goal
| Validation | Critical + High bug arrival rate trending down for the last X weeks(5) | Critical + High severity bug arrival rate trends
| Validation |  | Critical + High bug arrivals last week (ww n) |  | < ww n-1
| Validation |  | Critical + High bug arrivals two weeks ago (ww n-1) |  | < ww n-2
| Validation |  | Critical + High bug arrivals three weeks ago (ww n-2) |  | < ww n-3
| Validation | Validation report published | Validation Beta status report published |  | Done
| External Documentation | All External Documents are at accuracy level requested by marketing for Beta | External documents status
| External Documentation |  | # of external Alpha documents that needs updating |  | <number>
| External Documentation |  | % of external Alpha documents updated |  | 100%
| External Documentation |  | Number of external documents needed for Beta |  | <number>
| External Documentation |  | % of Beta external documents ready for release |  | 100%
| Internal Documentation | All Engineering Documents are completed for all the product's features, including DCRS | Engineering documents status(6)
| Internal Documentation |  | # of Alpha documents that needs updating |  | <number>
| Internal Documentation |  | % of Alpha documents updated |  | 100%
| Internal Documentation |  | # of documents planned for Beta |  | <number>
| Internal Documentation |  | % of documents planned for Beta completed |  | 100%
| Build & Release | Build & Release systems updated for Beta | Build & Release systems status
| Build & Release |  | Release labeled and virus scanned |  | Done
| Build & Release |  | % beta features that have CI tests |  | <number>
| Build & Release |  | ... Add lines for other infrastructure elements used in your organization |  | Meeting the goal
| Customer Support | Customer support is prepared for the release | Customer support preparation status
| Customer Support |  | Support plan updated, reviewed and published
| Customer Support |  | Customer support resources allocated and trained on Beta features |  | Done
| Customer Support |  | Release notes drafted, reviewed and ready for publication |  | Done
| Customer Support |  | ... Add lines for other documents or tools needed by customer support in your organization |  | Meeting the goal
Notes
| 1 | May also be stated as real goal (e.g. < 30mSec; > 10mbps; etc.)
| 2 | For example: throughput; transaction time; CPU utilization; memory utilization; power consumption; etc.
| 3 | Decide where to lump Alpha new features. They can go together with the Beta features (that is, track here all new features for this release); the can be lumped with the Legacy features; they can get their own rows with tighter targets than Beta new features.
| 4 | The percentage goal should be lower if this is a maintenance release VS an upgrade release
| 5 | Recommended: for at least the last 3 weeks What is considered a "trend" is up to the individual case. Is a drop of 1 discovered bug per week considered a trend? If you have a 4 bugs in week n-3, 3 in week n-2 and 2 in week n-1, the answers is likely to be "yes"; if the count is 20, 19, 18… probably no.
| 6 | Consider listing the different document types (requirement, design, architecture etc.) for tracking at higher granularity
All rights reserved © Michael Stahl 2016

## Gold
| Milestone | Program | Release date goal
| Gold | <program name> | <ww date>
Owner | Function | Requirement | Metric | Status | Goal
| PLC | All requirements from previous milestone continue to be satisfied | Beta Requirements status
| PLC |  | All Beta Release Requirements are met |  | Done
| PLC |  | All waivers granted at Beta are closed (requirement are now met) |  | Done
| PLC | Code freeze since Release date - X weeks | No code changes since the set date (X weeks prior to release date) |  | Done
| PLC | Staffing and plan in place for sustaining the product post-release | Sustaining plan approved and published to document repository <provide link> |  | Done
| HW | HW is Feature Complete and Fully Functional on production SKU | Feature support status
| HW |  | Total # features planned |  | <number>
| HW |  | # features blocked by HW |  | 0
| HW |  | % of features blocked by HW |  | 0%
| HW | HW Test Execution | HW test execution status
| HW |  | All HW tests (including Q&R) performed |  | Done
| HW |  | All HW test reports published |  | Done
| HW |  | All HW issues filed |  | Done
| HW | HW Quality | HW bugs status: Number or Critical and High HW issues open |  | Project-dependent
| HW |  | # open Critical HW issues |  | 0
| HW |  | # open High HW issues |  | 0
|  |  | # of open HW issues (total number) |  | <Z
| HW | HW bug discovery trends down | HW bug trends over last X weeks
| HW |  | # of new bugs opened in the last X weeks is trending down (each week less than the previous week) |  | Yes
| HW |  | Total number of HW bugs is trending down |  | Yes
| SW | All features are "code complete", including all Design Change Requests (DCRs) | Feature development status
| SW |  | % of product features and DCRs that are coded and merged into the main branch |  | 100%
| SW |  | % of product features pass unit level testing |  | 100%
| SW |  | % of Integration tests PASSED (on all target Operating Systems) |  | 100%
| SW |  | Formal code inspection complete |  | Done
| SW |  | Static analysis complete; All errors and warnings reviewed and dispositioned |  | Done
| SW |  | Unit level testing reports for all product features published |  | Done
| SW |  | Integration test report published |  | Done
| SW |  | Formal code inspection report published |  | Done
| SW |  | All debug and test code removed or hidden |  | Done
| Validation | Full backward compatibility to previous generation HW | % of supported HW that was tested |  | 100%
| Localization | Localization of all GUI, User Guides Help and support tools that are planned to be localized, is completed. | Localization status
| Localization |  | Number of languages planned to be supported by the final product |  | <number>
| Localization |  | % of the languages that are supported |  | 100%
| Localization |  | % of localized builds (including GUI, User Guides and Help) validated for both translation accuracy and functionality under localized OS |  | 100%
| Localization |  | Number of product support tools to be localized |  | <number>
| Localization |  | % of product support tools that are localized |  | 100%
| Performance | Performance is meeting the Gold targets | 100% of Gold release goal(1)
| Performance |  | ... Add lines for different performance parameters that are of interest for your product(2) |  | Meeting the goal
| Regulatory | External regulatory testing cycle completed | Regulatory test status
| Regulatory |  | % Regulatory testing complete |  | 100%
| Regulatory |  | Regulatory test report (including gap analysis) published |  | Done
| Regulatory |  | Corrective action published (if necessary) |  | Done
| Validation | All Test plans completed and updated to reflect approved DCRs | Test planning status
| Validation |  | project level test plan updated, reviewed and published |  | Done
| Validation |  | # of feature-level test plans planned for gold features |  | <number>
| Validation |  | % of feature-level test plans that are completed, reviewed and approved |  | 100%
| Validation |  | # of DCR approved and call for an update of test plans |  | <number>
| Validation |  | % of DCR-related updates to test plans that are completed, reviewed and approved |  | 100%
| Validation | All tests are traceable to product requirements | % of test cases mapped to product requirement |  | 100%
| Validation | Full test cycle completed | Test cycle and OS/HW combination test coverage status
| Validation |  | # of tests planned |  | <number>
| Validation |  | % of planned tests that were completed |  | 100%
| Validation |  | Number of different OS-Platform-SKU combinations that were planned to be covered on Gold test cycles |  | <number>
| Validation |  | % of different Gold-target OS-Platform-SKU combinations that were tested |  | 100%
| Validation | < X% failing / blocked tests per new feature | Test execution status - new features(3)
| Validation |  | Total number of new features targeted for Gold |  | <number>
| Validation |  | Number of new Gold features tested |  | All the product's new features
| Validation |  | Number of new Gold features completely blocked |  | 0
| Validation |  | Number of new Gold features with fail / block rate > 75% |  | 0
| Validation |  | Number of new Gold features with fail / block rate between 50% and 75% |  | 0
| Validation |  | Number of new Gold features with fail / block rate between 25% and 50% |  | 0
| Validation |  | Number of new Gold features with fail / block rate < 25% |  | <number>
| Validation | < Y% failing / blocked tests per legacy feature | Test execution status - legacy features(4)
| Validation |  | Total number of legacy features targeted for Gold |  | <number>
| Validation |  | Number of legacy Gold features tested |  | All the product's legacy features
| Validation |  | Number of legacy Gold features completely blocked |  | 0
| Validation |  | Number of legacy Gold features with fail / block rate > 75% |  | 0
| Validation |  | Number of legacy Gold features with fail / block rate between 50% and 75% |  | 0
| Validation |  | Number of legacy Gold features with fail / block rate between 25% and 50% |  | 0
| Validation |  | Number of legacy Gold features with fail / block rate < 25% |  | <number>
| Validation | No Critical bugs | Critical severity bug count |  | 0
| Validation | No High severity bugs | High severity bug count |  | 0
| Validation | < Z total bugs | Total bug count |  | <number>
| Validation | Total Bug Projection Model | Total Open bugs(5) |  | <number>
| Validation |  | Time remaining to fix bugs (weeks to Release date) |  | <number>
| Validation |  | Projected Bug submit rate per week (default is 3 week historical average) |  | <number>
| Validation |  | Projected Bug closure rate per week (default is 3 week historical average) |  | <number>
| Validation |  | Projected Open bugs at Release date |  | =F98+(F100-F101)*F99
| Validation | Specific features test & bug counts | % test execution completed and bug count for specific features
| Validation |  | <add lines as needed for features for which there are specific quality requirements. E.g. "100% tests executed and no critical or High severity bugs on Install/Uninstall" > |  | Meeting the goal
| Validation | Critical + High bug arrival rate trending down for the last X weeks(6) | Critical + High severity bug arrival rate trends
| Validation |  | Critical + High bug arrivals last week (ww n) |  | < ww n-1
| Validation |  | Critical + High bug arrivals two weeks ago (ww n-1) |  | < ww n-2
| Validation |  | Critical + High bug arrivals three weeks ago (ww n-2) |  | < ww n-3
| Validation | Validation report published | Validation Gold report published |  | Done
| External Documentation | All External Documents are at accuracy level requested by marketing for product release | External documents status
| External Documentation |  | Number of external documents needed for the release |  | <number>
| External Documentation |  | % of external documents ready for release |  | 100%
| Internal Documentation | All Engineering Documents are completed for all the product's features, including DCRS | Engineering documents status(7)
| Internal Documentation |  | # of documents planned |  | <number>
| Internal Documentation |  | % of documents completed |  | 100%
| Build & Release | Build & Release systems updated for Gold | Build & Release systems status
| Build & Release |  | Release labeled and virus scanned |  | Done
| Build & Release |  | % Gold features that have CI tests |  | <number>
| Build & Release |  | ... Add lines for other infrastructure elements used in your organization |  | <number>
| Customer Support | Customer support is prepared for the release | Customer support preparation status
| Customer Support |  | Support plan updated, reviewed and published
| Customer Support |  | Customer support resources allocated and trained on Gold features |  | Done
| Customer Support |  | Release notes drafted, reviewed and ready for publication |  | Done
| Customer Support |  | ... Add lines for other documents or tools needed by customer support in your organization |  | Done
Notes
| 1 | May also be stated as real goal (e.g. < 30mSec; > 10mbps; etc.)
| 2 | For example: throughput; transaction time; CPU utilization; memory utilization; power consumption; etc.
| 3 | Decide where to lump Alpha and Beta new features. They can go together with the Gold features (that is, track here all new features for this release); the can be lumped with the Legacy features; they can get their own rows with tighter targets than Beta new features.
| 4 | The percentage goal should be lower if this is a maintenance release VS an upgrade release
| 5 | Decide if to include Localization and Documentation bugs
| 6 | Recommended: for at least the last 3 weeks What is considered a "trend" is up to the individual case. Is a drop of 1 discovered bug per week considered a trend? If you have a 4 bugs in week n-3, 3 in week n-2 and 2 in week n-1, the answers is likely to be "yes"; if the count is 20, 19, 18… probably no.
| 7 | Consider listing the different document types (requirement, design, architecture etc.) for tracking at higher granularity
All rights reserved © Michael Stahl 2016

## Shorter, One-page option
Release Criteria | Pre-Alpha | Alpha | Beta | Gold | Owner | Comments
Project level quality target definition
Static analysis | Acceptable warnings defined
Unit test |  | Required unit-test coverage for Beta defined | Required unit-test coverage for Gold defined
Defect trends |  | Beta required "trend down" rate defined Beta "maximum up-trend" for total bugs defined | Gold required "trend down" rate defined Gold "maximum up-trend" for total bugs defined
Minimal test cycle |  |  | Contents of "minimal Gold test cycle" defined
SW Development
Architecture spec | Done | Updated to reflect changes | Updated to reflect changes and DCRs | Updated to reflect the final product
Design | Done for pre-alpha features | Done for alpha features | Done for all features | Updated to reflect the final product
Coding | Code complete for pre-alpha features | Code complete for alpha features | Code complete for all features | Code not changed for enough time to run the agreed upon minimal Gold test cycle
Unit test | Done for pre-alpha features | Done for alpha features | Done for all the code to the agreed upon coverage level | Done for all the code to the agreed upon coverage level
Design Changes |  |  | Implemented | Implemented
Static analysis | System in place for automated scan of all the code. First scan done. | Done on all the code with 0 critical issues | Done on all the code with 0 Critical and High issues | Done on all the code with no issues and only agreed upon warnings
Validation
Open Bugs count
Critical |  | ≤ X Priority 1 ≤ Y (all priorities) | ≤ X Priority 1 ≤ Y (all priorities) | 0 (all priorities)
High |  | ≤ Z | ≤ Z | 0
Total |  | ≤ W | ≤ W | ≤ X
Release to Release Bug trends (last 3 releases)
Critical |  |  | Trending down; meets the agreed upon rate | Trending down; meets the agreed upon rate
High |  |  | Trending down; meets the agreed upon rate | Trending down; meets the agreed upon rate
Total |  |  | Trending down; meets the agreed upon rate | Trending down; meets the agreed upon rate
Test execution
Executed tests (% of planned) | BAT | ≥X% | ≥X% | ≥X%
Passed tests (% of planned) | BAT passing with no blocked issues | ≥Y% | ≥Y% | ≥Y%
Features with more than 25% tests blocked |  | ≤ Z | ≤ Z | 0
Covered platforms | Primary platform, primary OS | Primary platform with all target OS Other platforms with primary OS | All target platforms with all target OS | All target platforms with all target OS
HW used | Engineering Samples (pre-alpha version) | Engineering Samples (alpha version) | Pre-production samples | Production samples
Performance, Power, KPIs
<parameter A> | Requirements defined and plan for measurement is in place | Values measured and plan is in place to meet Beta goals | ≥85% Gold Requirements | Meet Gold goals
<parameter B> | Requirements defined and plan for measurement is in place | Values measured and plan is in place to meet Beta goals | ≥85% Gold Requirements | Meet Gold goals
<parameter C> | Requirements defined and plan for measurement is in place | Values measured and plan is in place to meet Beta goals | ≥85% Gold Requirements | Meet Gold goals
… etc. (add line for each parameter relevant to your product) | … | … | … | …
Test Plans and Test management
Component Test Plan | Component Test Plan (CTP) is post peer-review for all pre-alpha features | CTP is post stakeholders review for all alpha features | All CTPs updated to reflect changes and actual test activities | All CTPs updated to reflect changes and actual test activities
Requirements coverage | Traceability in place between tests and pre-alpha requirements ≥85% pre-alpha requirements have at least one test linked to it | Traceability in place between tests and alpha requirements ≥90% alpha requirements have at least one test linked to it | Traceability in place between tests and beta requirements Each beta requirement has at least one test linked to it | Traceability in place between tests and requirements Each product requirement has at least one test linked to it
Test case management system | Pre-alpha planned test cases in the Test Management system | Alpha planned test cases in Test Management system | All test cases in Test Management system | All test cases in Test Management system
Test report | Test report for pre-alpha published | Test report for alpha published | Test report for beta published | Test report for Gold published
Build and Release
Source control | All pre-alpha code is in source control system | All alpha code is in source control system | All beta code is in source control system | All the release code is in source control system
Label | All source files are labeled in the Source control system | All source files are labeled in the Source control system | All source files are labeled in the Source control system | All source files are labeled in the Source control system
CI | Plan for implementation of CI is in place | All alpha features have at least one test in the CI system | All beta features have at least X tests in the CI system | All features have at least X tests in the CI system
Binaries metadata | Binaries have correct versioning info, copyright text, company, product name, etc. | Binaries have correct versioning info, copyright text, company, product name, etc. | Binaries have correct versioning info, copyright text, company, product name, etc. | Binaries have correct versioning info, copyright text, company, product name, etc.
"First article" | Package created successfully, installs successfully and has the correct unique versioning info | Package created successfully, installs successfully and has the correct unique versioning info | Package created successfully, installs successfully and has the correct unique versioning info | Package created successfully, installs successfully and has the correct unique versioning info
Virus check | Any released article is virus-checked | Any released article is virus-checked | Any released article is virus-checked | Any released article is virus-checked
Documentation
Release notes/manuals | Pre-alpha release notes produced and reviewed. Correct binaries versions in the release notes. | Alpha release notes produced and reviewed. Correct binaries versions in the release notes. | Beta release notes produced and reviewed. Correct binaries versions in the release notes. | Product release notes produced and reviewed. Correct binaries versions in the release notes.
User manual |  | User manual for alpha produced and reviewed | User manual for beta produced and reviewed | Final version of user manual produced and reviewed
API guide |  | API guide for alpha produced and reviewed | API guide for beta produced and reviewed | Final version of API guide produced and reviewed
… add lines for specific documents you want to track; or: collapse all lines into one general line about documentation
All rights reserved © Michael Stahl 2016

## Additional notes
Depending on your product and industry, consider adding lines to the QRC lists that track the status of the following areas:
Legal aspects
Contractual aspects
Certifications of all kind (FCC, CE, Microsoft HLK, Bluetooth, Wi-Fi Alliance, etc. etc.)
Regulatory requirements
Security aspects
HW sources (e.g. 2nd source)
Usability studies
Distribution (e.g. web sites readiness)
Marketing readiness
3rd party readiness
Sample code quality; sample apps functionality and performance
Errata lists
Support tools (e.g. tools needed by ISVs, HW manufacturers, end users to validate the final product works on their systems; product maintenance tools)
Backwards compatibility (HW, SW)
All rights reserved © Michael Stahl 2016